PROJECT PROPOSAL

CADSES Programme

- Call 2005 -

Project full title: Knowledge-Net Of Social Inclusion for Security

Project acronym: K.N.O.S.I.S.

Priority: 1 - Promoting spatial development approaches and actions for social and economic cohesion

Measure: 1.4 – Spatial impact of immigration

Lead partner (institution): University of Trento – Faculty of Engineering, IT Dept.

Lead partner (country): Italy

Deadline for application:  2005

Project Aim:

The general objective of the project is the development of spatial security through social inclusion and opportunities. In particular, the project aims at managing the spatial impact of immigrants, with special reference to female immigrants. This will be done through the creation of a community of interest, which works through a network of “comprehensive net-points/agencies”, both in Eastern and Western European countries. This network deals with information/support in all fields related to migration (i.e., administrative, labour, social, economic-financial, legislative, cultural issues).

This intervention is two-fold: it fosters integration of immigrants in the destination countries on one side, and it improves living conditions in the countries of origin on the other.

Project Objectives:

- Increasing and sharing knowledge on problems/needs connected with social security brought about by immigration, with specific reference to female immigrants, both within the countries of origin and destination (WP2);

- Promoting connections between countries of origin and destination of immigrants, with specific reference to female immigrants, through a network of “comprehensive net-points/agencies” (WP3);

- Facilitating communication and the exchange of (all kinds of) information on fields of essential importance for immigrants, with specific reference to female immigrants (WP4);

- Enabling local personnel to work within the “comprehensive net-points/agencies” (WP5).

Work packages:

WP1

Objective: project management

Actions:

1.1 Coordination and administrative management

Responsible: University of Trento – Faculty of Engineering, IT Dept. (Trento, Italy)

Participating partners: / /

1.2 Monitoring and evaluation (use of external/internal-evaluation methodology)

Responsible partners: European Monitoring Centre on Racism and Xenophobia, Vienna, Austria; European Migration Centre, Berlin, Germany

Participating partners: all partners

Activities:

1.2.1 Monitoring

1.2.2 Evaluation (intermediate, final)

WP2

Objective: research on social security problems and needs of immigrants, with particular reference to female immigrants (countries of origin), immigrants and resident population (destination countries) and explore the relation “immigration and social security” in the countries involved by the identification of social security needs.

Actions:

2.1 research on economic and financial issues (leading partner: TISE, Warsaw, Poland)

2.2 research on labour issues (leading partner: Ministry of Social Affairs, Zagreb, Croatia)

2.3 research on administrative-organisational-legal issues (CARITAS, Munich, Germany)

2.4 research on social issues (CARITAS, Brno, Czech Rep.)

2.5 research on cultural issues (ATAS, Trento, Italy)

Responsible partner: …

Participating partners: all partners will be involved in research data and information gathering on-site through their local networks

WP3

Objective: building a network of local/national “comprehensive net-points/agencies” working in different fields of support to immigrants-to-be and immigrants, with specific reference to female immigrants

Actions:

3.1 creation of “comprehensive points/agencies” to be linked in a network

3.2 creation of the network on economic and financial issues (leading partner: TISE, Warsaw, Poland)

3.3 creation of the network on labour issues (leading partner: Ministry of Social Affairs, Zagreb, Croatia)

3.4 creation of the network on administrative-organisational-legal issues (CARITAS, Munich, Germany)

3.5 creation of the network on social issues (CARITAS, Brno, Czech Rep.)

3.6 creation of the network on cultural issues (ATAS, Trento, Italy)

Responsible partner: ATAS (Trentino Association for Foreigners’ Welcome)

Participating partners: all partners (each one of them with a leading role in a specific field of support, as identified above 3.2-3.5)

WP4

Objective: construction of an IT network as an instrument for the “comprehensive net-points/agencies” network to work

Actions:

4.1 research on the IT (technical) model

4.2 research on the IT (knowledge) model

4.3 research on the IT (services) model

4.4 implementation of the models

Responsible partner: University of Trento – Faculty of Engineering, IT Dept.

Participating partners: all partners as for the implementation phase

WP5

Objective: training of professionals working within the “comprehensive net-points/agencies”

Actions:

5.1 training of professionals for the management of the “comprehensive net-points/agencies”

5.2 training partners for the use of the IT product

Responsible partner: University of Trento – Faculty of Engineering, IT Dept.

Participating partners: each partner individually as for action 5.1

WP6

Objective: information/promotion and dissemination of results

Actions:

6.1 Information/promotion of project’s activities

6.1.1 Workshops/seminars

6.1.2 Local/national meetings

6.1.3 International meetings

6.1.4 Meetings with local/national public authorities

6.2 Dissemination of results

6.2.1 Publications (policy paper, books, articles)

6.2.2 Final international conference

Responsible partner: Trentino Federation of Cooperatives

Participating partners: all partners through their own networks

Contacts:

Anna Alexeva: annaalexeva@atas.tn.it

Enrico BLANZIERI: blanzier@dit.unitn.it

Tanya: tanyayat@dit.unitn.it.

# Footnotes

Social security means the control of markets related to the immigrants’ needs (e.g., information, communication, financial remittance, administrative issues, etc.) potentially exploitable by criminals.